## 2017
		Huzzar Daze ?16-18?Jun2017 - General Organisation

		Task	Organiser	Status, comments
		Overall coordinator	Pete Anderson
		Letter to Hussar Village AMO	P.Anderson, K.Dundas	notification of use of campground, parade, etc
		Insurance		cover events, Lions Internt'l wanted to be insured (no)
		Security company	Pete Anderson	Beer gardens, dance
		Cash handling	Carry Taubert will do dance	Kathy Dundas will do final tally in July
		Advertising	Kathy Dundas	mailing 8.5*14", posted at Post Office, Sundowners

		Baseball tournament, Fri-Sun	Kyle Gordon & Wes Kirkpatrick
		garbage bin	Pete Anderson
		concession stand	trip kids	cook burgers, hot dogs, tacos, etc
		porta-potties	Pete Anderson	1,500$ ?? - big expense, get two
		water stands, hand soap	P.Anderson + B.Howell	Lions owns - warehouse @ grounds
		wash toilets every night	Bill Howell

		Breakfast, Saturday ?08:30-10:00?	Pete Sanden crew	setup, cook, clean - Leroy, K.Williams, W.Dundas, Fandry, Willard, Steve Fandry, everybody
		Parade, Sat 11:00-12:00		Canada 150th & Lions 100th
		Marshall	Ben Armstrong & Sandy Vicic	???
		BBQ, Sat 12:00-14:00??	Kidney - pay us $300	not Friends E.Whtld (Jadene Gregory)
		Craft fair at school	Sandy Vicic, Diane Taubert	?Maybe Sundowners will run?
		Equipment show, Sat 12:00-15:00??	Robert Knudsen	(tabled 28Mar2017), separate from parade

		Dance
		bar crew	Lions crews ?? & ??	2 crews for dance, beer garden shifts
		cash crew	replace <K. Dundas>
		workers (??)	Wendy Kaiser
		band	Wendy Kaiser	done - Drew Gregory (1.5k$ in 2016 ??)
		beer & liquor	Wayne Dundas	Wayne will get liquor & supplies for bar & beer gardens (negotiate with Ray), bar crews will handle
		liquor license	Pete Anderson	done in Jan-Feb
		midnight food	Kidney Foundation / (food truck?)	Treacy Anderson, Lisa Armstrong ?beef on a bun, pay bun with tickets?
		clean hall	trip kids	plus food
		generator set	<Peter Sanden>

		Children's events
		bouncing balls, castle	Kathy Dundas call	<850$ for package by company> Pete Sanden will arrange funding (Treacy, Minor baseball, Hussar Playschool, Fish&Game)
		4H club horses	Ag Society separate event	Terea Sandum is doing it again
		other ?	If extra $ - Rosebud magician Lothbar, face painting	NO - greased pig race, scavenger hunt, cowboy robbery, etc

		Beer gardens, Sat 12-18:00, Sun 12-18:00
		volunteers	Bill Howell	needs 2 more crews
		tent from Strandard	Pete Anderson	already ordered
		liquor licence	Pete Anderson	done in Jan-Feb
		karaoke	Marianne Oxtoby	28Mar - P.Anderson confirmed with Marianne
		trailer, genset, for beer gardens	Glen Muller
		freezer	purchase Yvonne Comstock's freezer	Kathy Dundas arranged

x	x	x	x	x	x

## 2016
		Huzzar Daze 17-19Jun2016 - General Organisation
		17-19Jun2016
		Task	Organiser	Status, comments

		Overall coordinator	Pete Anderson

		Letter to Hussar Village AMO	Kathy Dundas	notification of use of campground, parade, etc - insurances

		Baseball tournament, Fri-Sun	?Cole Kaiser or Clay Armstrong?	was Kevin Slemko - not this year
		garbage bin	Pete Anderson
		concession stand
		porta-potties	Pete Anderson	1,500$ ?? - big expense, get two
		water stands, hand soap	Pete Anderson?	Lions owns - warehouse @ grounds

		Breakfast, Saturday ?08:30-10:00?

		Parade, Sat 11:00-12:00		NOT Rust & Shine - next year
		Marshall	?Ben Anderson?	Kathy will get him?
		Hussar school grads

		BBQ, Sat 12:00-14:00??	Kathy Dundas	run by Hall Board? (Kirstin) / Friends of East Wheatland - form of donation?

		Craft fair at school

		Equipment show, Sat 12:00-15:00??	Robert Kirkpatrick

		Dance
		bar crew	Lions crews ?? & ??
		cash crew	???
		workers (??)	Wendy Kaiser
		band	Wendy Kaiser	Drew Gregory has been booked (1,500 $ ??) / his poster is ready 12Apr2016
		beer & liquor		was Wayne Dundas, for bar & beer gardens
		midnight food	?Yvonne?	beef on a bun, pay bun with tickets (Clay Armstrong), BIG bun (Caathy Dundas)
		clean hall	trip kids	plus food
		generator set	Peter Sanden

		Farewell to school
		Children's events
		"Cocoons-inflated balls" to run around in	Wendy Kaiser
		greased pig race	?	?Glen Muller?
		?mini-fair, magician, castle?		850$ for package by company
		?Scavenger hunt?
		sponsor		Pete Sanden to find a sponsor

		Beer gardens, Sat 12-18:00, Sun 12-18:00
		volunteers	Bill Howell
		tent from Strathmore	Kathy Dundas	22Mar2016 - already booked
		liquor licence	Pete Anderson	08Feb2016 - Mounties haven't signed yet
		karaoke	Marianne Oxtoby

x	x	x	x	x	x